## NMA - 1T 2013
Ressource | Projet | Jour | Date
|  | mardi | 2013-01-01
|  | mercredi | 2013-01-02
|  | jeudi | 2013-01-03
|  | vendredi | 2013-01-04
|  | samedi | 2013-01-05
|  | dimanche | 2013-01-06
|  | lundi | 2013-01-07
|  | mardi | 2013-01-08
|  | mercredi | 2013-01-09
|  | jeudi | 2013-01-10
|  | vendredi | 2013-01-11
|  | samedi | 2013-01-12
|  | dimanche | 2013-01-13
|  | lundi | 2013-01-14
|  | mardi | 2013-01-15
|  | mercredi | 2013-01-16
|  | jeudi | 2013-01-17
|  | vendredi | 2013-01-18
|  | samedi | 2013-01-19
|  | dimanche | 2013-01-20
Nicolas | REUNICA//[P2] Batch GEC/Validation/Planification 1 (jour : 1) | lundi | 2013-01-21
Nicolas | REUNICA//[P2] Batch GEC/Validation/Planification 1 (jour : 2) | mardi | 2013-01-22
Nicolas | REUNICA//[P2] Batch GEC/Validation/Planification 1 (jour : 3) | mercredi | 2013-01-23
Nicolas | REUNICA//[P2] Batch GEC/Validation/Planification 1 (jour : 4) | jeudi | 2013-01-24
Nicolas | REUNICA//[P2] Batch GEC/Validation/Planification 1 (jour : 5) | vendredi | 2013-01-25
|  | samedi | 2013-01-26
|  | dimanche | 2013-01-27
Nicolas | REUNICA//[INTERSIS] Batch import BCN/Validation/Planification 1 (jour : 1) | lundi | 2013-01-28
Nicolas | REUNICA//[INTERSIS] Batch import BCN/Validation/Planification 1 (jour : 2) | mardi | 2013-01-29
Nicolas | REUNICA//[INTERSIS] Batch import BCN/Validation/Planification 1 (jour : 3) | mercredi | 2013-01-30
Nicolas | REUNICA//[P2]Montée en charge P2 tir1/Validation/Planification 1 (jour : 1) | jeudi | 2013-01-31
Nicolas | REUNICA//[P2]Montée en charge P2 tir1/Validation/Planification 1 (jour : 2) | vendredi | 2013-02-01
|  | samedi | 2013-02-02
|  | dimanche | 2013-02-03
Nicolas | REUNICA//[P2]Montée en charge P2 tir1/Validation/Planification 1 (jour : 3) | lundi | 2013-02-04
|  | mardi | 2013-02-05
|  | mercredi | 2013-02-06
|  | jeudi | 2013-02-07
|  | vendredi | 2013-02-08
|  | samedi | 2013-02-09
|  | dimanche | 2013-02-10
|  | lundi | 2013-02-11
|  | mardi | 2013-02-12
|  | mercredi | 2013-02-13
|  | jeudi | 2013-02-14
|  | vendredi | 2013-02-15
|  | samedi | 2013-02-16
|  | dimanche | 2013-02-17
|  | lundi | 2013-02-18
|  | mardi | 2013-02-19
|  | mercredi | 2013-02-20
Nicolas | REUNICA//[P2]Montée en charge P2 tir2/Validation/Planification 1 (jour : 1) | jeudi | 2013-02-21
Nicolas | REUNICA//[P2]Montée en charge P2 tir3/Validation/Planification 1 (jour : 1) | vendredi | 2013-02-22
|  | samedi | 2013-02-23
|  | dimanche | 2013-02-24
Nicolas | REUNICA//[P2]Montée en charge P2 tir4/Validation/Planification 1 (jour : 1) | lundi | 2013-02-25
Nicolas | REUNICA//[P2]Montée en charge P2 tir5/Validation/Planification 1 (jour : 1) | mardi | 2013-02-26
|  | mercredi | 2013-02-27
Nicolas | REUNICA//[P2]Montée en charge P2 tir6/Validation/Planification 1 (jour : 1) | jeudi | 2013-02-28
|  | vendredi | 2013-03-01
|  | samedi | 2013-03-02
|  | dimanche | 2013-03-03
Nicolas | REUNICA//[P2]Montée en charge P2 tir7/Validation/Planification 1 (jour : 1) | lundi | 2013-03-04
|  | mardi | 2013-03-05
|  | mercredi | 2013-03-06
Nicolas | REUNICA//[P2]Montée en charge P2 tir8/Validation/Planification 1 (jour : 1) | jeudi | 2013-03-07
|  | vendredi | 2013-03-08
|  | samedi | 2013-03-09
|  | dimanche | 2013-03-10
Nicolas | REUNICA//[P2]Montée en charge P2 tir9/Validation/Planification 1 (jour : 1) | lundi | 2013-03-11
|  | mardi | 2013-03-12
|  | mercredi | 2013-03-13
|  | jeudi | 2013-03-14
|  | vendredi | 2013-03-15
|  | samedi | 2013-03-16
|  | dimanche | 2013-03-17
|  | lundi | 2013-03-18
|  | mardi | 2013-03-19
|  | mercredi | 2013-03-20
|  | jeudi | 2013-03-21
|  | vendredi | 2013-03-22
|  | samedi | 2013-03-23
|  | dimanche | 2013-03-24
|  | lundi | 2013-03-25
|  | mardi | 2013-03-26
|  | mercredi | 2013-03-27
|  | jeudi | 2013-03-28
|  | vendredi | 2013-03-29
|  | samedi | 2013-03-30
|  | dimanche | 2013-03-31

## XRO - 1T 2013
Ressource | Projet | Jour | Date
|  | mardi | 2013-01-01
|  | mercredi | 2013-01-02
|  | jeudi | 2013-01-03
|  | vendredi | 2013-01-04
|  | samedi | 2013-01-05
|  | dimanche | 2013-01-06
|  | lundi | 2013-01-07
|  | mardi | 2013-01-08
|  | mercredi | 2013-01-09
|  | jeudi | 2013-01-10
|  | vendredi | 2013-01-11
|  | samedi | 2013-01-12
|  | dimanche | 2013-01-13
|  | lundi | 2013-01-14
|  | mardi | 2013-01-15
|  | mercredi | 2013-01-16
|  | jeudi | 2013-01-17
|  | vendredi | 2013-01-18
|  | samedi | 2013-01-19
|  | dimanche | 2013-01-20
Xavier | REUNICA//[P2] Lanceur EXCEL ESIC/Conception/Développement/Planification 1 (jour : 1) | lundi | 2013-01-21
Xavier | REUNICA//[P2] Lanceur EXCEL ESIC/Conception/Développement/Planification 1 (jour : 2) | mardi | 2013-01-22
Xavier | REUNICA//[P2] Lanceur EXCEL ESIC/Conception/Développement/Planification 1 (jour : 3) | mercredi | 2013-01-23
Xavier | REUNICA//[P2] Batch interface mouvements PTF/Conception/Planification 1 (jour : 1) | jeudi | 2013-01-24
Xavier | REUNICA//[P2] Batch interface mouvements PTF/Conception/Planification 1 (jour : 2) | vendredi | 2013-01-25
|  | samedi | 2013-01-26
|  | dimanche | 2013-01-27
Xavier | REUNICA//[P2] Batch interface mouvements PTF/Conception/Planification 1 (jour : 3) | lundi | 2013-01-28
Xavier | REUNICA//[P2] Batch interface mouvements PTF/Conception/Planification 1 (jour : 4) | mardi | 2013-01-29
Xavier | REUNICA//[P2] Batch interface mouvements PTF/Conception/Planification 1 (jour : 5) | mercredi | 2013-01-30
Xavier | REUNICA//[P2] Batch interface mouvements PTF/Développement/Planification 1 (jour : 1) | jeudi | 2013-01-31
Xavier | REUNICA//[P2] Batch interface mouvements PTF/Développement/Planification 1 (jour : 2) | vendredi | 2013-02-01
|  | samedi | 2013-02-02
|  | dimanche | 2013-02-03
Xavier | REUNICA//[P2] Batch interface mouvements PTF/Développement/Planification 1 (jour : 3) | lundi | 2013-02-04
Xavier | REUNICA//[P2] Batch interface mouvements PTF/Développement/Planification 1 (jour : 4) | mardi | 2013-02-05
Xavier | REUNICA//[P2] Batch interface mouvements PTF/Développement/Planification 1 (jour : 5) | mercredi | 2013-02-06
Xavier | REUNICA//[P2] Batch interface mouvements PTF/Développement/Planification 1 (jour : 6) | jeudi | 2013-02-07
Xavier | Congé de Xavier (jour : 1) | vendredi | 2013-02-08
|  | samedi | 2013-02-09
|  | dimanche | 2013-02-10
Xavier | Congé de Xavier (jour : 2) | lundi | 2013-02-11
Xavier | Congé de Xavier (jour : 3) | mardi | 2013-02-12
Xavier | REUNICA//[P2] Batch interface mouvements PTF/Développement/Planification 1 (jour : 7) | mercredi | 2013-02-13
Xavier | REUNICA//[P2] Batch interface mouvements PTF/Validation/Planification 1 (jour : 1) | jeudi | 2013-02-14
|  | vendredi | 2013-02-15
|  | samedi | 2013-02-16
|  | dimanche | 2013-02-17
|  | lundi | 2013-02-18
|  | mardi | 2013-02-19
|  | mercredi | 2013-02-20
|  | jeudi | 2013-02-21
|  | vendredi | 2013-02-22
|  | samedi | 2013-02-23
|  | dimanche | 2013-02-24
|  | lundi | 2013-02-25
|  | mardi | 2013-02-26
|  | mercredi | 2013-02-27
|  | jeudi | 2013-02-28
Xavier | REUNICA//[LINK] Lanceur graphique/Spécification/Planification 1 (jour : 1) | vendredi | 2013-03-01
|  | samedi | 2013-03-02
|  | dimanche | 2013-03-03
Xavier | REUNICA//[LINK] Lanceur graphique/Spécification/Planification 1 (jour : 2) | lundi | 2013-03-04
Xavier | REUNICA//[LINK] Lanceur graphique/Spécification/Planification 1 (jour : 3) | mardi | 2013-03-05
Xavier | REUNICA//[LINK] Lanceur graphique/Spécification/Planification 1 (jour : 4) | mercredi | 2013-03-06
Xavier | REUNICA//[LINK] Lanceur graphique/Spécification/Planification 1 (jour : 5) | jeudi | 2013-03-07
Xavier | REUNICA//[LINK] Lanceur graphique/Spécification/Planification 1 (jour : 6) | vendredi | 2013-03-08
|  | samedi | 2013-03-09
|  | dimanche | 2013-03-10
Xavier | REUNICA//[LINK] Lanceur graphique/Conception/Planification 1 (jour : 1) | lundi | 2013-03-11
Xavier | REUNICA//[LINK] Lanceur graphique/Conception/Planification 1 (jour : 2) | mardi | 2013-03-12
Xavier | REUNICA//[LINK] Lanceur graphique/Conception/Planification 1 (jour : 3) | mercredi | 2013-03-13
Xavier | REUNICA//[LINK] Lanceur graphique/Conception/Planification 1 (jour : 4) | jeudi | 2013-03-14
Xavier | REUNICA//[LINK] Lanceur graphique/Conception/Planification 1 (jour : 5) | vendredi | 2013-03-15
|  | samedi | 2013-03-16
|  | dimanche | 2013-03-17
Xavier | REUNICA//[LINK] Lanceur graphique/Développement/Planification 1 (jour : 1) | lundi | 2013-03-18
Xavier | REUNICA//[LINK] Lanceur graphique/Développement/Planification 1 (jour : 2) | mardi | 2013-03-19
Xavier | REUNICA//[LINK] Lanceur graphique/Développement/Planification 1 (jour : 3) | mercredi | 2013-03-20
Xavier | REUNICA//[LINK] Lanceur graphique/Développement/Planification 1 (jour : 4) | jeudi | 2013-03-21
Xavier | REUNICA//[LINK] Lanceur graphique/Développement/Planification 1 (jour : 5) | vendredi | 2013-03-22
|  | samedi | 2013-03-23
|  | dimanche | 2013-03-24
Xavier | REUNICA//[LINK] Lanceur graphique/Développement/Planification 1 (jour : 6) | lundi | 2013-03-25
Xavier | REUNICA//[LINK] Lanceur graphique/Validation/Planification 1 (jour : 1) | mardi | 2013-03-26
Xavier | REUNICA//[LINK] Lanceur graphique/Validation/Planification 1 (jour : 2) | mercredi | 2013-03-27
Xavier | REUNICA//[LINK] Lanceur graphique/Validation/Planification 1 (jour : 3) | jeudi | 2013-03-28
|  | vendredi | 2013-03-29
|  | samedi | 2013-03-30
|  | dimanche | 2013-03-31

## YBA - 1T 2013
Ressource | Projet | Jour | Date
|  | mardi | 2013-01-01
|  | mercredi | 2013-01-02
|  | jeudi | 2013-01-03
|  | vendredi | 2013-01-04
|  | samedi | 2013-01-05
|  | dimanche | 2013-01-06
|  | lundi | 2013-01-07
|  | mardi | 2013-01-08
|  | mercredi | 2013-01-09
|  | jeudi | 2013-01-10
|  | vendredi | 2013-01-11
|  | samedi | 2013-01-12
|  | dimanche | 2013-01-13
|  | lundi | 2013-01-14
|  | mardi | 2013-01-15
|  | mercredi | 2013-01-16
|  | jeudi | 2013-01-17
|  | vendredi | 2013-01-18
|  | samedi | 2013-01-19
|  | dimanche | 2013-01-20
Yohan | REUNICA//[P2] Batch interface mouvements PTF/Spécification/Planification 1 (jour : 1) | lundi | 2013-01-21
Yohan | REUNICA//[P2] Batch interface mouvements PTF/Spécification/Planification 1 (jour : 2) | mardi | 2013-01-22
Yohan | REUNICA//[P2] Batch interface mouvements PTF/Spécification/Planification 1 (jour : 3) | mercredi | 2013-01-23
Yohan | REUNICA//[P2] Batch interface mouvements PTF/Spécification/Planification 1 (jour : 4) | jeudi | 2013-01-24
Yohan | REUNICA//[P2] Batch interface mouvements PTF/Spécification/Planification 1 (jour : 5) | vendredi | 2013-01-25
|  | samedi | 2013-01-26
|  | dimanche | 2013-01-27
Yohan | REUNICA//[P2] Batch interface mouvements PTF/Spécification/Planification 1 (jour : 6) | lundi | 2013-01-28
Yohan | REUNICA//[P2] Batch interface mouvements PTF/Spécification/Planification 1 (jour : 7) | mardi | 2013-01-29
Yohan | REUNICA//[P2] Batch Interface mouvements Organisation/Spécification/Planification 1 (jour : 1) | mercredi | 2013-01-30
Yohan | REUNICA//[P2] Batch Interface mouvements Organisation/Spécification/Planification 1 (jour : 2) | jeudi | 2013-01-31
Yohan | REUNICA//[P2] Batch Interface mouvements Organisation/Spécification/Planification 1 (jour : 3) | vendredi | 2013-02-01
|  | samedi | 2013-02-02
|  | dimanche | 2013-02-03
Yohan | REUNICA//[P2] Batch Interface mouvements Organisation/Spécification/Planification 1 (jour : 4) | lundi | 2013-02-04
Yohan | REUNICA//[P2] Batch Interface mouvements Organisation/Spécification/Planification 1 (jour : 5) | mardi | 2013-02-05
Yohan | REUNICA//[P2] Batch Interface mouvements Organisation/Spécification/Planification 1 (jour : 6) | mercredi | 2013-02-06
Yohan | REUNICA//[P2] Batch Interface mouvements Organisation/Spécification/Planification 1 (jour : 7) | jeudi | 2013-02-07
Yohan | REUNICA//[P2] Batch Interface mouvements Organisation/Spécification/Planification 1 (jour : 8) | vendredi | 2013-02-08
|  | samedi | 2013-02-09
|  | dimanche | 2013-02-10
Yohan | REUNICA//[2UR] SMOG Multi-BCB/Spécification/Planification 1 (jour : 1) | lundi | 2013-02-11
Yohan | REUNICA//[2UR] SMOG Multi-BCB/Spécification/Planification 1 (jour : 2) | mardi | 2013-02-12
Yohan | REUNICA//[2UR] SMOG Multi-BCB/Spécification/Planification 1 (jour : 3) | mercredi | 2013-02-13
Yohan | REUNICA//[2UR] SMOG Multi-BCB/Spécification/Planification 1 (jour : 4) | jeudi | 2013-02-14
Yohan | REUNICA//[2UR] SMOG Multi-BCB/Spécification/Planification 1 (jour : 5) | vendredi | 2013-02-15
|  | samedi | 2013-02-16
|  | dimanche | 2013-02-17
Yohan | REUNICA//[2UR] SMOG Multi-BCB/Conception/Planification 1 (jour : 1) | lundi | 2013-02-18
Yohan | REUNICA//[2UR] SMOG Multi-BCB/Conception/Planification 1 (jour : 2) | mardi | 2013-02-19
Yohan | REUNICA//[2UR] SMOG Multi-BCB/Conception/Planification 1 (jour : 3) | mercredi | 2013-02-20
Yohan | REUNICA//[2UR] SMOG Multi-BCB/Conception/Planification 1 (jour : 4) | jeudi | 2013-02-21
Yohan | REUNICA//[2UR] SMOG Multi-BCB/Conception/Planification 1 (jour : 5) | vendredi | 2013-02-22
|  | samedi | 2013-02-23
|  | dimanche | 2013-02-24
Yohan | REUNICA//[2UR] SMOG Multi-BCB/Développement/Planification 1 (jour : 1) | lundi | 2013-02-25
Yohan | REUNICA//[2UR] SMOG Multi-BCB/Développement/Planification 1 (jour : 2) | mardi | 2013-02-26
Yohan | REUNICA//[2UR] SMOG Multi-BCB/Développement/Planification 1 (jour : 3) | mercredi | 2013-02-27
Yohan | REUNICA//[2UR] SMOG Multi-BCB/Développement/Planification 1 (jour : 4) | jeudi | 2013-02-28
Yohan | REUNICA//[2UR] SMOG Multi-BCB/Développement/Planification 1 (jour : 5) | vendredi | 2013-03-01
|  | samedi | 2013-03-02
|  | dimanche | 2013-03-03
Yohan | REUNICA//[2UR] SMOG Multi-BCB/Validation/Planification 1 (jour : 1) | lundi | 2013-03-04
Yohan | REUNICA//[2UR] SMOG Multi-BCB/Validation/Planification 1 (jour : 2) | mardi | 2013-03-05
Yohan | REUNICA//[2UR] SMOG Multi-BCB/Validation/Planification 1 (jour : 3) | mercredi | 2013-03-06
Yohan | REUNICA//[2UR] SMOG Multi-BCB/Validation/Planification 1 (jour : 4) | jeudi | 2013-03-07
Yohan | REUNICA//[2UR] SMOG Multi-BCB/Validation/Planification 1 (jour : 5) | vendredi | 2013-03-08
|  | samedi | 2013-03-09
|  | dimanche | 2013-03-10
|  | lundi | 2013-03-11
|  | mardi | 2013-03-12
|  | mercredi | 2013-03-13
|  | jeudi | 2013-03-14
|  | vendredi | 2013-03-15
|  | samedi | 2013-03-16
|  | dimanche | 2013-03-17
|  | lundi | 2013-03-18
|  | mardi | 2013-03-19
|  | mercredi | 2013-03-20
|  | jeudi | 2013-03-21
|  | vendredi | 2013-03-22
|  | samedi | 2013-03-23
|  | dimanche | 2013-03-24
|  | lundi | 2013-03-25
|  | mardi | 2013-03-26
|  | mercredi | 2013-03-27
|  | jeudi | 2013-03-28
|  | vendredi | 2013-03-29
|  | samedi | 2013-03-30
|  | dimanche | 2013-03-31